## Instructions
Project Risk Register Template
Purpose | Capture material project risks in one controlled register so sponsors can see exposure, ownership and action status.
How to use | Enter each risk as a future uncertain event. Score probability and impact from 1 low to 5 high. The risk score multiplies both fields.
Review rhythm | Review high-priority risks weekly and all other open risks at every governance meeting.
Scoring guidance | 1 to 5 = Low, 6 to 12 = Medium, 15 to 25 = High. Adjust thresholds if your governance standard differs.
Note | This template is a working management tool. Adapt terminology and thresholds to your organization before use.

## Risk Register
Risk ID | Project | Risk Description | Category | Cause | Potential Impact | Probability | Impact | Risk Score | Priority | Mitigation Action | Contingency Action | Risk Owner | Due Date | Status | Last Reviewed | Notes
R-001 | Client portal launch | Key subject matter expert unavailable during testing | People | Competing operational commitments | Defects may be discovered late | 3 | 4 | 0 | High | Agree named backup and protected review windows | Move low-risk features to next release | Project Manager | 2026-09-15 | Open | Review weekly
R-002 | Client portal launch | Integration dependency not confirmed | Technical | Vendor timeline unclear | Launch scope may reduce | 2 | 5 | 0 | Medium | Secure written dependency date and interface owner | Prepare manual upload workaround | Technology Lead | 2026-09-20 | Open | Escalate if unchanged
R-003 | Client portal launch | Users unclear on new workflow | Change | Training not scheduled | Adoption may be slow | 3 | 3 | 0 | Medium | Run role-based briefing before launch | Extend hypercare support | Change Lead | 2026-09-25 | Planned | Add to readiness plan